**Attachment C – Activity Work Plan**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Subrecipient | City of Lakeland |  | Activity: | Lake Bonnet Drainage Flood Hazard and Debris Mitigation Project |  | Project Budget: | $42,986,390.00 |
| Contract Number: | MT047 |  | Date Prepared: | February 6, 2024 |  | Modification Number: | 2 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Start Date**(month/year) | **End Date**(month/year) | **Describe Proposed Action to be Completed by the “End Date.”*****Examples of Actions:*** *Procure Administrator or Engineer, Complete Environmental Review and Obtain Release of Funds, Request Wage Decision, Complete and Submit Design and Specifications, Advertise for and Open Bids, Issue Notice to Proceed, Construction Completion (33, 66, and 100 percent or 25, 50, 75, and 100 percent), Complete Construction Procurement Process, Advertise Availability of Housing Rehabilitation Funds, Complete Rankings of Homes per HAP, Number of Houses Rehabilitated and Submit Closeout Package to DEO.*  |  **Estimated Units to be Completed by the “End Date”** | **Estimated Funds to be Requested by the“End Date”** |
| 11/22 | 10/28 | 1a. Financial records maintenance, preparation, and submittal of monthly and quarterly reports, HUD reports, SERA forms, and Audit reports | 96 | $1,593,290.96 |
| 12/23 | 10/28 | 1b. Conduct stakeholder meetings (with property owners within the project area) and prepare meeting minutes. Provide community engagement and outreach activities, public meetings, and information sharing via social media and/or other methods as outlined in DOC Agreement No MT047 Project implementation through Phase 1, Phase 2, and Phase 3 | 12 | $347,163.12 |
| 12/22 | 12/23 | 1c. Prepare and submit bid documents and specifications for environmental consulting services, including NEPA review, program oversight, project design, and engineering, for review and approval by DOC | 1 | $40,000 |
| 1/23 | 12/23 | 1c. Advertise for and open bids for environmental consulting services, evaluate and rank bids, issue notice to proceed to selected subcontractor, prepare contract documents | 1 | $10,000 |
| 12/22 | 10/28 | 1d. Monthly project planning meetings with City staff, vendors, subcontractors, and regulatory agencies, and preparation and submittal of meeting minutes to City and DOC as outlined in DEO Agreement No. MT047 Project Implementation through Phase 1, Phase 2, and Phase 3 (estimated 72 months) | 72 | $989,443.39 |
| 6/24 | 12/24 | 1e. Complete NEPA review (field investigations, records review, and site surveys) | 1 | $174,942,41 |
| 9/24 | 11/24 | 1f. Prepare and submit NEPA/Findings and Recommendations Report (DRAFT) | 1 | $57,369.90 |
| 11/24 | 12/24 | 1f. Prepare and submit NEPA Findings and Recommendations Report (FINAL) | 1 | $54,746.50 |
| 11/23 | 10/28 | 1g. Project Oversight and Program Management, communications with regulatory agencies, QA/QC oversight, compliance maintenance, etc., as outlined in DOC Agreement No MT047 Project Implementation through Phase 1, Phase 2, and Phase 3 | 72 | $2,092,098.11 |
| 11/23 | 12/24 | 2d. Stakeholder coordination with property owners within the Feasibility Study project area to obtain site access and review the scope of work | 1 | $27,811.25 |
| 12/23 | 04/24 | 2a. Floodway Encroachment Analysis (field investigations, records review, and site visits) | 4 | $273,900.19 |
| 04/24 | 05/24 | 2a. Prepare and submit DRAFT Floodway Encroachment Analysis report with findings and recommendations | 1 | $39,865.77 |
| 05/24 | 06/24 | 2a. Prepare and submit FINAL Floodway Encroachment Analysis report with findings and recommendations | 1 | $18,134.17 |
| 12/23 | 04/24 | 2b. Complete FEMA review and coordination, prepare Letter of Map Revision (as needed) | 3 | $14,676.95 |
| 12/23 | 05/24 | 2c. Complete pre-application meetings with permitting agencies, including Southwest Florida Water Management District (SWFWMD), Florida Department of Environmental Protection (FDEP), US Army Corp of Engineers (USACoE) | 4 | $19,937.37 |
| 12/23 | 04/24 | 2e. Conduct surveys, site inspections, property records review, property appraisals, and land/easement acquisition study | 5 | $53,159.67 |
| 12/23 | 04/24 | 2f. Prepare and submit project technical scope, schedule, budget review, and refinement to DOC for approval | 3 | $60,354.83 |
| 12/23 | 03/24 | 2g. Complete Topographic & Boundary Survey of the project study area | 2 | $71,559.06 |
| 12/23 | 04/24 | 2h. Complete Wetlands Delineation in project study area  | 1 | $87,153.44 |
| 12/23 | 04/24 | 2i. Complete Bathymetric Mapping and Sediment Thickness Survey  | 2 | $181,751.77 |
| 12/23 | 04/24 | 2j. Complete LiDAR Survey of project study area | 1 | $55,938.31 |
| 04/24 | 05/24 | 2k. Complete Project Feasibility Study & Implementation Plan DRAFT report  | 2 | $198,196.82 |
| 05/24 | 06/24 | 2k. Complete Project Feasibility Study & Implementation Plan FINAL report | 2 | $42,564.22 |
| 5/24 | 6/24 | 2l. Complete and submit 30% Preliminary Design Report for Dredge Operations, Wetland Rehabilitation, and Littoral Zone Restoration  | 3 | $201,772.45 |
| 5/24 | 6/24 | 2m. Complete and submit 30% Preliminary Design Report for Flood Protection Mitigation | 1 | $193,920.66 |
| 11/23 | 1/25 | 3a. Complete easement and property acquisitions (budget includes sub-consultant time and $$ to purchase property) | 20 | $278,237.73 |
| 06/24 | 05/25 | 3b. Complete Work Plans for field investigation work, including Health & Safety Plan, Emergency Response Plan, Sampling & Analysis Plan, and Quality Assurance Project Plan | 4 | $108,160.72 |
| 7/24 | 11/25  | 3c. Complete sediment sampling field investigation, laboratory analysis, and summary report | 3 | $324,075.00 |
| 7/24 | 02/26 | 3d. Complete geotechnical field investigation, laboratory analysis, and summary report | 3 | $193,606.33 |
| 7/24 | 2/25 | 3e. Complete groundwater impact field investigation (monitoring well and seepage meter install, sampling, and laboratory analysis) and summary report | 5 | $146,746.95 |
| 7/24 | 3/25 | 3f. Complete treatability testing/evaluation and summary report | 3 | $96,495.98 |
| 2/25 | 5/25 | 3g. Complete Construction Design Plans (60%) for Dredge Operations, Wetland Restoration, and Littoral Zone Rehabilitation | 3 | $219,138.74 |
| 6/25 | 7/25 | 3l. Complete Construction Design Plans (60%) for Flood Protection Mitigation | 1 | $209,871.10 |
| 8/24 | 9/25 | 3j. Complete Value Engineering & Constructability Review and Summary Report | 3 | $60,023.80 |
| 9/25 | 11/25 | 3h. Complete Construction Design Plans (90%) for Dredge Operations, Wetland Restoration, and Littoral Zone Rehabilitation | 3 | $137,290.86 |
| 9/25 | 11/25 | 3m. Complete Construction Design Plans (90%) for Flood Protection Mitigation, and submit to DEO for review | 1 | $154,485.12 |
| 07/24 | 07/25 | 3k. State, Local, and Federal Permit application and submittals (SWFWMD, FDEP, USACoE, and Building) | 4 | $93,611.07 |
| 12/25 | 01/26 | 3i. Complete Construction Design Plans (100%) for Dredge Operations, Wetland Restoration, and Littoral Zone Rehabilitation | 3 | $84,961.60 |
| 12/25 | 01/26 | 3n. Complete Construction Design Plans (100%) for Flood Protection Mitigation | 1 | $77,490.69 |
| 02/26 | 03/26 | 3o. Complete Construction Design and Bid Specification Package for Dredge Operations, Wetland Restoration and Littoral Zone Rehabilitation and submit to DEO for review and approval | 1 | $112,707.74 |
| 02/26 | 03/26 | 3p. Complete Construction Design and Bid Specification Package for Flood Protection Mitigation and submit to DEO for review and approval | 1 | $124,306.82 |
| 03/26 | 04/26 | 4a. Construction bid notifications for dredging operations and sediment management, subcontractor site visit, bid review, bid award & notification to the most responsive bidder(s). Complete procurement package and submit to DEO for review and approval | 4 | $45,000 |
| 03/26 | 04/26 | 4m. Construction bid notification for flood protection mitigation (weir removal, embankment stabilization, pump station construction, culvert retrofits, canal modifications, and flood relief diversion infrastructure), subcontractor site visit, bid review, bid award & notification to most responsive bidder(s). Complete the procurement package and submit it to DEO for review and approval. | 4 | $53,007.18 |
| 02/25 | 03/26 | 4c. Complete construction oversight work plans (Health & Safety, Emergency Response & Preparedness) | 3 | $51,786.10 |
| 05/25 | 10/28 | 4b. Construction Management & Vendor/Subcontractor Oversight, monthly project status review/updates as outlined in DOC Agreement No MT047 throughout Phase 3 | 48 | $1,834,500.87 |
| 5/25 | 10/28 | 4d. Lake Bonnet sediment removal/dredging equipment mobilization | 3 | $418,000 |
| 11/28 | 10/28 | 4l. Lake Bonnet sediment removal/dredging equipment demobilization | 3 | $418,000 |
| 5/25 | 10/28 | 4e. Construct dredge materials management area(s) (DMMA) and dewatering operations for contaminated sediment | 1 | $540,830 |
| 5/25 | 10/28 | 4f. Construct geocells and aquadams for non-contaminated sediment | 1 | $600,000 |
| 5/25 | 10/28 | 4g. Lake Bonnet sediment dredging operations, separation of contaminated vs. non-contaminated sediment (approximately 425,000 cubic yards) | 1 | $2,790,179 |
| 6/25 | 10/28 | 4h. Emplace non-contaminated sediment in geocells and complete wetland rehabilitation | 1 | $6,696,429 |
| 6/25 | 10/28 | 4i. Emplace contaminated sediment in DMMA and complete dewatering operations | 1 | $230,000 |
| 6/25 | 10/28 | 4j. Loading/transport/disposal of approximately 58,000 cubic yards of contaminated sediment (includes laboratory analysis, manifest preparation, and tracking) | 1 | $2,232,140 |
| 6/25 | 10/28 | 4k. Thin layer sand capping and littoral zone restoration | 1 | $1,116,071 |
| 8/25 | 10/25 | 4n. Demolition of dilapidated weir in Bonnet Canal | 1 | $198,329 |
| 6/25 | 6/26 | 4o. Regrading and stabilization of the west Lake Bonnet embankment | 1 | $2,016,000 |
| 6/26 | 6/27 | 4p. Construct and install pump station, 42” force main, and ancillary equipment for pumping water from Lake Bonnet Canal to Lake Bonnet | 1 | $2,135,196 |
| 6/27 | 8/27 | 4q. Install pump station power drop | 1 | $40,000 |
| 1/25 | 6/27 | 4r. Retrofit/construct culverts at May Manor Crossing | 1 | $457,380 |
| 1/25 | 6/27 | 4s. Retrofit/construct culverts at Bridge Boulevard | 1 | $457,380 |
| 1/25 | 6/27 | 4t. Lake Bonnet Canal modifications/retrofit (excavation, bank stabilization, dewatering, transport and disposal of materials) | 1 | $2,215,080 |
| 1/25 | 06/28 | 4u. Construction of flood relief diversion barriers, conveyance infrastructure, and retention/detention facilities | 1 | $8,926,255 |
| 6/25 | 06/28 | 4v. Final Report delivery, including as-built engineering drawings and photo documentation. | 1 | $193,865.28 |